## Requirements
Requirements
Select the best one using a multi-weighted scoring model
Calculate implementation time and to prepare resources plans for the selected project
Recommend a strategy to reduce implementation time for the selected project.

## Project1
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	None	5	10	6	45
D	A	6	18	7	50
E	D	8	26	8	80
F	D	4	45	12	150
G	D	3	60	10	180
H	C,E	2	15	4	100
I	G	1	12	2	30

## Project2
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	A	5	10	6	45
D	A	6	18	7	50
E	A	8	26	8	80
F	A	4	45	12	150
G	B, C	3	60	10	180
H	F, G	2	15	4	100
I	D	1	12	2	30

## Project3
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	B	5	10	6	45
D	B	6	18	7	50
E	A, C	8	26	8	80
F	A, C	4	45	12	150
G	A, C	3	60	10	180
H	D, G	2	15	4	100
I	E	1	12	2	30

## Project4
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	None	5	10	6	45
D	A	6	18	7	50
E	B, D	8	26	8	80
F	B, D	4	45	12	150
G	B, D	3	60	10	180
H	C, E	2	15	4	100
I	G	1	12	2	30

## Project5
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	A	5	10	6	45
D	A	6	18	7	50
E	A	8	26	8	80
F	A	4	45	12	150
G	B, C	3	60	10	180
H	F, G	2	15	4	100
I	E, H	1	12	2	30

## Project6
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	None	5	10	6	45
D	A	6	18	7	50
E	C	8	26	8	80
F	C	4	45	12	150
G	B, D, E	3	60	10	180
H	B, D, E	2	15	4	100
I	F, H	1	12	2	30

## Criteria
Criteria Weight	ROI	Stay with core competencies	Defect reduction	Sale improvement	Customer loyalty improvement	Environmental friendly
	0.25	0.1	0.3	0.2	0.1	0.05
Project 1	10	6	8	7	9	8
Project 2	7	9	6	8	8	7
Project 3	10	8	7	9	9	8
Project 4	8	8	9	6	7	6
Project 5	9	9	6	8	8	9
Project 6	6	8	9	8	6	6