## Requirements
Requirements
Select the best one using a multi-weighted scoring model					OK
Calculate implementation time and to prepare resources plans for the selected project
	Implementation Time					OK
	Resources Anticipated					OK
		Labour Resource				OK
		Machine Resource				OK
		Capital Resource				OK
	Resource Prepare
Recommend a strategy to reduce implementation time for the selected project.

## Project1
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	None	5	10	6	45
D	A	6	18	7	50
E	D	8	26	8	80
F	D	4	45	12	150
G	D	3	60	10	180
H	C,E	2	15	4	100
I	G	1	12	2	30

## Project2
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	A	5	10	6	45
D	A	6	18	7	50
E	A	8	26	8	80
F	A	4	45	12	150
G	B, C	3	60	10	180
H	F, G	2	15	4	100
I	D	1	12	2	30

## Project3
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	B	5	10	6	45
D	B	6	18	7	50
E	A, C	8	26	8	80
F	A, C	4	45	12	150
G	A, C	3	60	10	180
H	D, G	2	15	4	100
I	E	1	12	2	30

## Project3Network
Legend
					8	F	12
ES	ID	EF					5	Description
SL	Description					13	4	17
LS	Dur	LF
					0	A	2
					6
					6	2	8				8	E	16				16	I	17
					0					0
					8	8	16				16	1	17

					3	C	8
					0
					3	5	8				8	G	11
	0	B	3					4
	0					12	3	15
	0	3	3
					3	D	9
					6
					9	6	15
					11	H	13
					4
					15	2	17

## Project3LabourSchedule
Labour Schedule

Activity	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	SL	ST	DUR	LS	CO
B	8	8	8	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	3	0	8
C	0	0	0	10	10	10	10	10	0	0	0	0	0	0	0	0	0	0	3	5	3	10
E	0	0	0	0	0	0	0	0	26	26	26	26	26	26	26	26	0	0	8	8	8	26
I	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	12	0	16	1	16	12
G	0	0	0	0	0	0	0	0	60	60	60	0	0	0	0	0	0	4	8	3	12	60
H	0	0	0	0	0	0	0	0	0	0	0	15	15	0	0	0	0	4	11	2	15	15
F	0	0	0	0	0	0	0	0	45	45	45	45	0	0	0	0	0	5	8	4	13	45
A	6	6	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	6	0	2	6	6
D	0	0	0	18	18	18	18	18	18	0	0	0	0	0	0	0	0	6	3	6	9	18
SUM	14	14	8	28	28	28	28	28	149	131	131	86	41	26	26	26	12
Labour Demand
Weeks
Labour

## Project3MachineSchdule
Machine Schedule

Activity	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	SL	ST	DUR	LS	CO
B	6	6	6	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	3	0	6
C	0	0	0	6	6	6	6	6	0	0	0	0	0	0	0	0	0	0	3	5	3	6
E	0	0	0	0	0	0	0	0	8	8	8	8	8	8	8	8	0	0	8	8	8	8
I	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	2	2	16	1	16	2
G	0	0	0	0	0	0	0	0	10	10	10	0	0	0	0	0	0	4	8	3	12	10
H	0	0	0	0	0	0	0	0	0	0	0	4	4	0	0	0	0	4	11	2	15	4
F	0	0	0	0	0	0	0	0	12	12	12	12	0	0	0	0	0	5	8	4	13	12
A	4	4	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	6	0	2	6	4
D	0	0	0	7	7	7	7	7	7	0	0	0	0	0	0	0	0	6	3	6	9	7
SUM	10	10	6	13	13	13	13	13	37	30	30	24	12	8	8	8	2

## Project3BudgetSchedule
Budget Schedule

Activity	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	SL	ST	DUR	LS	CO
B	2	2	2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	3	0	6
C	0	0	0	1.2	1.2	1.2	1.2	1.2	0	0	0	0	0	0	0	0	0	0	3	5	3	6
E	0	0	0	0	0	0	0	0	1	1	1	1	1	1	1	1	0	0	8	8	8	8
I	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	2	2	16	1	16	2
G	0	0	0	0	0	0	0	0	3.33333333333333	3.33333333333333	3.33333333333333	0	0	0	0	0	0	4	8	3	12	10
H	0	0	0	0	0	0	0	0	0	0	0	2	2	0	0	0	0	4	11	2	15	4
F	0	0	0	0	0	0	0	0	3	3	3	3	0	0	0	0	0	5	8	4	13	12
A	2	2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	6	0	2	6	4
D	0	0	0	1.16666666666667	1.16666666666667	1.16666666666667	1.16666666666667	1.16666666666667	1.16666666666667	0	0	0	0	0	0	0	0	6	3	6	9	7
SUM	4	4	2	2.36666666666667	2.36666666666667	2.36666666666667	2.36666666666667	2.36666666666667	8.5	7.33333333333333	7.33333333333333	6	3	1	1	1	2
CUM	4	8	10	12.3666666666667	14.7333333333333	17.1	19.4666666666667	21.8333333333333	30.3333333333333	37.6666666666667	45	51	54	55	56	57	59

## Project4
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	None	5	10	6	45
D	A	6	18	7	50
E	B, D	8	26	8	80
F	B, D	4	45	12	150
G	B, D	3	60	10	180
H	C, E	2	15	4	100
I	G	1	12	2	30

## Project5
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	A	5	10	6	45
D	A	6	18	7	50
E	A	8	26	8	80
F	A	4	45	12	150
G	B, C	3	60	10	180
H	F, G	2	15	4	100
I	E, H	1	12	2	30

## Project6
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	None	5	10	6	45
D	A	6	18	7	50
E	C	8	26	8	80
F	C	4	45	12	150
G	B, D, E	3	60	10	180
H	B, D, E	2	15	4	100
I	F, H	1	12	2	30

## Criteria
Criteria Weight	ROI	Stay with core competencies	Defect reduction	Sale improvement	Customer loyalty improvement	Environmental friendly	Score
	0.25	0.1	0.3	0.2	0.1	0.05
Project 3	10	8	7	9	9	8	8.5
Project 1	10	6	8	7	9	8	8.2
Project 5	9	9	6	8	8	9	7.8
Project 4	8	8	9	6	7	6	7.7
Project 6	6	8	9	8	6	6	7.5
Project 2	7	9	6	8	8	7	7.2