## Requirements
Requirements
Select the best one using a multi-weighted scoring model					OK
Calculate implementation time and to prepare resources plans for the selected project
Recommend a strategy to reduce implementation time for the selected project.

## Project1
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	None	5	10	6	45
D	A	6	18	7	50
E	D	8	26	8	80
F	D	4	45	12	150
G	D	3	60	10	180
H	C,E	2	15	4	100
I	G	1	12	2	30

## Project2
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	A	5	10	6	45
D	A	6	18	7	50
E	A	8	26	8	80
F	A	4	45	12	150
G	B, C	3	60	10	180
H	F, G	2	15	4	100
I	D	1	12	2	30

## Project3
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	B	5	10	6	45
D	B	6	18	7	50
E	A, C	8	26	8	80
F	A, C	4	45	12	150
G	A, C	3	60	10	180
H	D, G	2	15	4	100
I	E	1	12	2	30

## Project3Network
Legend
					8	F	12
ES	ID	EF					5	Description
SL	Description					13	4	17
LS	Dur	LF
					0	A	2
					6
					6	2	8				8	E	16				16	I	17
					0					0
					8	8	16				16	1	17

					3	C	8
					0
					3	5	8				8	G	11
	0	B	3					4
	0					12	3	15
	0	3	3
					3	D	9
					6
					9	6	15
					11	H	13
					4
					15	2	17

## Project3Schedule
Labour Schedule

Activity	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16
A
B
C
D
E
F
G
H
I

## Project4
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	None	5	10	6	45
D	A	6	18	7	50
E	B, D	8	26	8	80
F	B, D	4	45	12	150
G	B, D	3	60	10	180
H	C, E	2	15	4	100
I	G	1	12	2	30

## Project5
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	A	5	10	6	45
D	A	6	18	7	50
E	A	8	26	8	80
F	A	4	45	12	150
G	B, C	3	60	10	180
H	F, G	2	15	4	100
I	E, H	1	12	2	30

## Project6
Project Activity	Precedent Activity	Time (week)	Labour (person/week)	Machine (unit/week)	Cost (Millions VND/week)
A	None	2	6	4	20
B	None	3	8	6	36
C	None	5	10	6	45
D	A	6	18	7	50
E	C	8	26	8	80
F	C	4	45	12	150
G	B, D, E	3	60	10	180
H	B, D, E	2	15	4	100
I	F, H	1	12	2	30

## Criteria
Criteria Weight	ROI	Stay with core competencies	Defect reduction	Sale improvement	Customer loyalty improvement	Environmental friendly	Score
	0.25	0.1	0.3	0.2	0.1	0.05
Project 3	10	8	7	9	9	8	8.5
Project 1	10	6	8	7	9	8	8.2
Project 5	9	9	6	8	8	9	7.8
Project 4	8	8	9	6	7	6	7.7
Project 6	6	8	9	8	6	6	7.5
Project 2	7	9	6	8	8	7	7.2